## Project Planner
VSADS Project
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ID | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1 | INITIALISING | 1 | 6 | 1 | 5 | 100% | bar: PERIODS 1 to PERIODS 6
1.1 | Establish project group and communication model | 1 | 1 | 1 | 1 | 100%
1.2 | Analyse problem requirements | 1 | 2 | 1 | 1 | 100%
1.3 | Define project scope | 3 | 2 | 2 | 1 | 100%
1.4 | Define project milestones, deliverables | 5 | 1 | 5 | 1 | 100%
1.5 | Allocate resources | 6 | 1 | 6 | 1 | 100%
2 | PLANNING | 6 | 7 | 6 | 6 | 100%
2.1 | Project Plan – detailed tasks, dependencies and timelines | 6 | 5 | 6 | 6 | 100%
2.2 | Risk Management | 11 | 2 | 11 | 1 | 100%
2.3 | Plan the development language/libraries and environment. | 11 | 2 | 11 | 2 | 100%
2.4 | Plan system architecture and software database schema. | 11 | 3 | 11 | 3 | 100%
2.5 | Define data source and integration | 11 | 1 | 11 | 1 | 100%
2.6 | Outline software design and Software components. | 11 | 2 | 11 | 1 | 100%
3 | EXECUTION | 13 | 13 | 13 | 15 | 0%
3.1 | Frontend | 13 | 5 | 13 | 4 | 80%
3.1.1 | Install web application components | 13 | 1 | 13 | 1 | 100%
3.1.2 | Establish web application environment | 14 | 1 | 15 | 1 | 100%
3.1.3 | Create main UI components | 15 | 3 | 15 | 4 | 90%
3.2 | Backend | 14 | 4 | 16 | 3 | 100%
3.2.1 | Perform necessary cleaning and optimization of the database | 14 | 1 | 16 | 1 | 100%
3.2.2 | Create table structure and import data. | 15 | 2 | 16 | 1 | 100%
3.2.3 | Establish link between database and middleware | 17 | 1 | 17 | 1 | 80%
3.3 | Data Integration | 18 | 6 | 17 | 3 | 100%
3.3.1 | Install SQL connector | 18 | 1 | 18 | 1 | 100%
3.3.2 | Establish extraction, transformation and loading processes. | 19 | 3 | 18 | 2 | 100%
3.3.3 | Establish a list of objects from the database and return to frontend | 22 | 2 | 21 | 3 | 100%
3.4 | CI/CD | 24 | 2 | 22 | 2 | 100%
3.5 | Documentation | 17 | 4 | 19 | 6 | 60%
4 | CONTROLLING | 18 | 9 | 23 | 7 | 0%
4.1 | Implement and enforce version control practices | 26 | 1 | 24 | 2 | 80%
4.2 | Track progress of project, referring back to established timelines | 24 | 1 | 25 | 1 | 100%
4.3 | Reviewing the project plan and software design document | 25 | 2 | 26 | 1 | 100%
4.4 | Concurrent unit and function testing and reporting | 18 | 5 | 26 | 2 | 30%
5 | CLOSING | 27 | 6 | 27 | 4 | 70%
5.1 | Produce user documentation | 27 | 3 | 27 | 2 | 70%
5.2 | Produce version control logs | 27 | 1 | 27 | 1 | 100%
5.3 | Produce close out documentation | 30 | 3 | 27 | 2 | 60%